## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kanderi Babu Trisha | 2025-09-03 | Missing values in Azure dataset causing NaN errors during preprocessing | Sprint 1 | Kanderi Babu Trisha | Data Issue | Implemented interpolation and mean imputation | 2025-09-04 | Closed | Dataset cleaned successfully
2 | Kanderi Babu Trisha | 2025-09-07 | ARIMA model failed due to non-stationary data | Sprint 2 | Kanderi Babu Trisha | Model Issue | Applied differencing and log transformation | 2025-09-08 | Closed | Model trained successfully after transformation
3 | Kanderi Babu Trisha | 2025-09-10 | API endpoint returning 500 error while serving forecasts | Sprint 3 | Kanderi Babu Trisha | Backend Bug | Fixed incorrect JSON serialization in Flask route | 2025-09-11 | Closed | API working fine post-fix
4 | Polu Vijay Kumar | 2025-09-14 | Graph not updating after selecting a new region on dashboard | Sprint 3 | Polu Vijay Kumar | Frontend Logic | Added async API call and setState handler | 2025-09-15 | Closed | Dashboard interactive and responsive now
5 | Kanderi Babu Trisha & Polu Vijay Kumar | 2025-09-18 | Forecast data mismatch between backend and frontend | Sprint 4 | Kanderi Babu Trisha & Polu Vijay Kumar | Integration Issue | Unified timestamp formats and re-tested endpoints | 2025-09-19 | Closed | Data alignment verified
6 | Kanderi Babu Trisha | 2025-09-21 | Dashboard takes long to load due to large data size | Sprint 4 | Kanderi Babu Trisha | Performance | Optimized backend queries and reduced payload size | 2025-09-22 | Closed | Load time improved by 60%
7 | Polu Vijay Kumar | 2025-09-23 | Chart.js tooltip showing wrong date labels | Sprint 4 | Polu Vijay Kumar | UI Bug | Updated Chart.js configuration | 2025-09-24 | Closed | Tooltip labels now accurate
8 | Kanderi Babu Trisha & Polu Vijay Kumar | 2025-09-25 | Minor rounding errors in CPU forecast output | Sprint 4 | Kanderi Babu Trisha & Polu Vijay Kumar | Model Output | Applied rounding logic in backend model output | 2025-09-26 | Closed | Predictions displaying correctly now